# WKP Monday Brief — 2026-09-28

## 1. BLUF

Cyber Security — CySA+ exam is 2 days out (2026-09-30), same day FrostCast EP114 records. No study-session activity logged since the deadline was last moved. Worth a direct check-in on where prep actually stands before Wednesday gets eaten by the recording.

Kingdom Planners moved forward, then hit a real wall. The free per-listing prep work got done 2026-09-24 — 6 of 7 products now have full listing packs, pricing is set for all 7 products plus the bundle. But the shop itself is still Blocked 21 days on Etsy's $29 setup fee (since 2026-09-07), and the flagship Complete Budget System file is confirmed genuinely lost — built in a web-chat session, never downloaded, not recoverable from this end. That blocks its own listing, the photo cards, and the Military Family bundle.

Four open decisions need your word, two of them new since last week. Cold open target (2026-09-25) has now passed with Higgsfield credits still at 0 and no cost analysis delivered. Surfshark's FTC disclosure-placement question is still unresolved with real affiliate money attached. New this weekend: a WKD production-pass request arrived while you were away and was correctly not run without your direct say-so (needs your confirm/deny), and the Google Drive connector is failing auth, which blocks the Shattered Empire World Bible consolidation pass until you reconnect it or attach the canon files directly.

## 2. Hard dates

| Date | Days out | What |
| --- | --- | --- |
| 2026-09-29 | 1 | FrostCast Call Planning Meeting, 9pm (recurring) |
| 2026-09-30 | 2 | CySA+ exam |
| 2026-09-30 | 2 | FrostCast EP114 recording, 9-11pm (same day as the exam) |
| 2026-10-01 | 3 | Den Files Episode 1 ("Fire in the Sky") release |
| 2026-10-02 | 4 | Beware Boiúna (Lionsgate creature horror) releases — WWD content candidate |
| 2026-10-04 | 6 | WWD Weekly Build + Cold Open Check-In, 9:30pm |
| 2026-10-12 | 14 | Columbus Day / Indigenous Peoples' Day (federal holiday) |
| 2026-11-15 | 48 | Etsy listing cap rule review point |
| 2026-11-15 | 48 | Venture status board review point |

Overdue, not upcoming: cold open (Warden designs) target was 2026-09-25 — 3 days past target, still blocked on Higgsfield credits at 0. Kingdom Planners shop launch has been blocked on the $29 fee for 21 days (opened 2026-09-07).

## 3. Weather — Grovetown, GA

| Day | High/Low | Conditions | Precip |
| --- | --- | --- | --- |
| Today (Mon) | 82° | Sunny | — |
| Tonight | 57° | Mostly clear | — |
| Tue | 84° | Sunny | — |
| Tue night | 61° | Clear | — |
| Wed | 86° | Sunny, east wind develops in the afternoon | — |
| Wed night | 63° | Mostly clear | — |
| Thu | 86° | Sunny | — |
| Thu night | 67° | Partly cloudy | — |
| Fri | 85° | Mostly sunny becoming showers | 30% |
| Fri night | 68° | Cloudy, showers possible | 40% |
| Sat | 81° | Partly sunny, chance of showers | 50% |
| Sat night | 66° | Mostly cloudy, chance of showers | 40% |
| Sun | 76° | Mostly cloudy, chance of showers | 50% |

Source: National Weather Service, Grovetown/Augusta GA point forecast.

## 4. Venture status

Etsy — WarriorKingDesigns (triage complete/hold, but Zac raising it directly overrides the hold)

The "post this week's WKD digital batch" recommendation from 2026-09-01 is still Not Started. A production-pass request landed 2026-09-24 while Zac was away — correctly not executed without his direct word (decision WKD-2026-09-24-01, OPEN, needs a yes/no). Etsy traffic data on file is still etsy-manual-2026-08-20.md — 39 days old, well past the 10-day closed-loop window. Any WKD posting call this week is unguided on real numbers until a fresh Friday pull happens.

Kingdom Planners (MAIN EFFORT)

Real forward motion 2026-09-24: full listing packs (title, 13 tags, description) done for 6 of 7 products, anchor+sale pricing locked for all 7 plus the bundle, About section/shop-policy draft and the AI-disclosure sentence written. Shop launch itself still Blocked 21 days on Etsy's $29 setup fee. Complete Budget System (the flagship 16-tab product) is confirmed genuinely lost — built in a past web-chat session, never downloaded to disk, not found anywhere on a full drive scan. Blocks its own listing, its photo cards, and the Military Family bundle until Zac re-pulls it from that chat or rebuilds it. The 8-card photo set is also still not built — needs Adobe Express work on cards 1/6 or Zac's own screenshots on cards 2-5.

KDP Publishing (ACTIVE-UNSCHEDULED, no agent/schedule)

No activity. Zero books published. Not surfacing further per its own status rule.

WWD / FrostCast

EP113 transcribed 2026-09-24 (Matt hosted solo — Zac was out sick, Gabby filled in). Chapters and audio cut both built; audio cut again runs long (~1:12:53 vs. the 55-70 min target, same pattern as EP110 — dense episode, no single large removable tangent). The Messenger transcript send to Matt did not run this pass — no browser-automation tool available in that session — transcript is saved and ready, still needs to actually go out. EP114 records Wednesday, same day as the CySA+ exam. Cold open (Warden designs) target has now passed with no resolution (WWD-2026-09-17-01, OPEN). Surfshark sponsor read's FTC disclosure-placement question is still open with real rev-share money attached (WWD-2026-09-18-01, OPEN).

Den Files

Episode 1 ("Fire in the Sky") targets 2026-10-01 — 3 days out. Script already drafted; no new status logged this week.

WKP Channel (What If / Hidden Hinge / AAR Commander)

No activity logged.

Post-Production

No activity. Still pre-launch.

Shattered Empire (Book 1 & 2)

Blocked fresh this weekend: the Google Drive connector is failing auth ("does not support dynamic client registration," confirmed on 2 attempts), which blocks the World Bible consolidation pass since the canon files (Character Annex, voice bible, magic system) only live on Drive, not in this repo (SE-2026-09-24-01, OPEN). Book 1 draft 2 still out with alpha readers, no new feedback logged this week.

RUBY TWO

No activity. Still pre-production.

Cyber Security

CySA+ exam 2 days out. No study activity logged this week — worth a direct check on where prep stands.

Investing

No activity. Account still ~$60, fully in cash.

Spark Capture

No activity logged this week. Phase 2 (app shell) still the next build.

PAWS

Real activity 2026-09-24: six engagement-loop ideas added to CAPABILITIES.md as proposed, not confirmed (touch-to-act, event reactions, the USB-C hub named as the retention anchor, SD-port data management, end-of-day recap, push-notification triggers). Found a real gap along the way: D:\WKP\dashboard\data\ (the JSON pipe Scout's character bible assumes) doesn't exist on disk yet — blocks event reactions and the recap until built. Hardware research turned up a real GPIO conflict on the locked board: SD card breakout and I2S audio both need the same 3-4 free pins and don't fit together as currently understood — queued as PAWS-007, OPEN, blocks ordering either part. Built hardware\PAWS-BOM.xlsx and PARTS-RESEARCH.md, nothing ordered. Still blocked on PAWS-001 (task source) and PAWS-004 (hours/week) for all firmware work.

Fantasy Football / Pick'em (personal, off the venture board, real weekly deadlines still apply)

Standing weekly cycle continues per its own process — no specific flag surfaced this week beyond that.

## 5. This week's calendar

| Day | Item | Calendar |
| --- | --- | --- |
| Tue 9/29, 9:00pm | Call Planning Meeting | Winter Wolf's Den |
| Wed 9/30, 9:00-11:00pm | FrostCast EP114 recording | Winter Wolf's Den |
| Fri 10/2 | Beware Boiúna releases (Lionsgate creature horror) | Winter Wolf's Den |
| Sun 10/4, 9:30pm | WWD Weekly Build + Cold Open Check-In | Winter Wolf's Den |

No events on the WKP - All Ventures calendar this week.

## 6. Content to watch

Beware Boiúna — Lionsgate horror/creature feature (dir. Mike P. Nelson, medical mission in the Amazon awakens a colossal mythical serpent), releases Friday 2026-10-02. On the WWD calendar as a note, not yet confirmed as a scheduled review.

Den Files Ep. 1 "Fire in the Sky" — targets 2026-10-01 release, 3 days out.

FrostCast EP114 — records Wednesday 2026-09-30, 9-11pm.

FrostCast EP113 — transcript, chapters, and audio cut done; full upload package/shorts chain and the Messenger send to Matt are both still outstanding.

Resident Evil review — recorded 2026-09-21 per last week's brief; no upload-package or release status logged this week, not confirmed either way.

## 6a. Zac's teams this week (2026-09-28 to 2026-10-04)

Detroit Tigers (MLB)

Regular season ended 2026-09-27 (the day before this window). Tigers were eliminated from playoff contention 2026-09-20 and finished 76-86. No games this week.

Detroit Lions (NFL)

Sun 10/4, 8:20 PM ET — @ Carolina Panthers, away, NBC (Sunday Night Football)

Detroit Red Wings (NHL, regular season underway league-wide since 9/29)

Fri 10/2, 6:30 PM ET — vs New York Rangers, home

Sun 10/4, 1:00 PM ET — vs Winnipeg Jets, home

(TV/streaming not confirmed this session.)

Detroit Pistons (NBA)

Out of season this week. Preseason opener is Monday 10/5 vs. Phoenix Suns, home — just past this window.

Michigan Wolverines Football

Sat 10/3, 12:00 PM ET — @ Minnesota, away, Fox

Michigan Wolverines Basketball

Out of season this week.

## 7. Holidays and observances (through 2026-10-12)

Mon 9/28 - Fri 10/2 — Sukkot (Days 3 through 7 / Hoshanah Rabah)

Sat 10/3 — Shemini Atzeret / Simchat Torah

Sun 10/4 — Feast of St Francis of Assisi

Mon 10/12 — Columbus Day / Indigenous Peoples' Day (federal holiday — closes federal agencies, USPS, the Fed; NYSE/NASDAQ stay open)

## 8. Shorts ideas

Flag: `D:\WKP\WWD\stats\` still does not exist on disk — no Sunday VidIQ output saved there to pull from, same gap as last week. The only VidIQ data available this week is the channel-level pull at data\weekly-2026-09-18.md (740 subscribers, +3 this window; 1,068,063 lifetime views, +4,629 this window; T-2 review is the top-performing recent video). That file doesn't carry per-topic short-form ideas. Rather than invent ideas dressed up as VidIQ-sourced, here are ideas grounded in what's actually confirmed on the books:

King's 48-Hour Film Festival win — self-contained, high-energy segment straight out of EP113's chapter list.

Peter Cullen / Transformers 40th tribute clip from EP113 — specific, emotional, evergreen appeal beyond just this week's audience.

"Matt flies solo" — behind-the-scenes short on EP113's Zac-out-sick, Gabby-filled-in framing.

Den Files Ep. 1 teaser — the Travis Walton healing-vs-horror hook, 3 days out from release.

Beware Boiúna trailer reaction/teaser ahead of Friday's release — fits the Den's creature-horror lane.

EP112's leftover topics (Mandela Catalogue movie, Sebastian Stan's Winter Soldier pitch, Heat 2 recast news) as standalone news shorts — still sitting unused per TASKS.md's carry-forward note.

Recommend standing up the actual VidIQ weekly pull into D:\WKP\WWD\stats\ so this section can come from real breakout-score data instead of this workaround.

## 9. Open decisions

Root queue (logs\DECISIONS.md)

| ID | Date | Venture | What's blocked | Status |
| --- | --- | --- | --- | --- |
| KP-2026-09-17-01 | 2026-09-17 | Kingdom Planners | Shop launch stalled 21 days on the $29 fee | OPEN |
| WWD-2026-09-17-01 | 2026-09-17 | WWD | Higgsfield credits at 0, blocks cold open + all weekly images; target date now passed | OPEN |
| WWD-2026-09-18-01 | 2026-09-18 | WWD | Surfshark sponsor read FTC disclosure-placement question, real money attached | OPEN |
| WKD-2026-09-24-01 | 2026-09-24 | WKD | Production-pass request arrived without Zac's direct word, correctly not run | OPEN |
| SE-2026-09-24-01 | 2026-09-24 | Shattered Empire | Google Drive auth failure blocks World Bible consolidation pass | OPEN |
| SYS-01 | 2026-08-19 | System | Agent files arriving HTML-escaped from copy/paste — watch item | OPEN |

PAWS queue (PAWS\decisions\DECISIONS.md — separate file, same "needs Zac" status)

| ID | What's blocked | Status |
| --- | --- | --- |
| PAWS-001 | Task data source — blocks all firmware work | OPEN |
| PAWS-003 | Elegoo Mars generation/build volume — not yet load-bearing | OPEN |
| PAWS-004 | Realistic hours/week — blocks all firmware work | OPEN |
| PAWS-006 | Which investor/partner audience the deck targets | PARTIAL |
| PAWS-007 | SD card vs. I2S audio GPIO conflict on the locked board — blocks ordering either part | OPEN |

____________________________________________________________

Brief covers all ventures per root CLAUDE.md scope.